## Sheet1
Stages | Activities | Start Date | Completetion Data | Status | 2020 - 2021
December 18 - January 15
[5 empty] | week 1 - 2 | week 2-3 | week 3-4
Project Planning | Kickoff Meeting | 2020-12-18 | 2020-12-18 | Done
| Research Analysis | 2020-12-21 | 2020-12-22 | Done
| Project Proposal | 2020-12-23 | 2020-12-24
| Signed-off | 2020-12-24 | 2020-12-24
Analysis Report | Project Defination Documentation
Analysis Report
Project Presentation
Iteration 1 | Database Design
UI Design
Identity Framework Implementation
UI Implementation
Iteration 2 | Admin Interface Implemenation
User Interface Implemenation
CRUD Implemenation
Testing
Closing | Report
Final Documentation
Presentation